## Control Sheet
Document Title | ISO IEC 27001 2022 Transition checklist
Document ID
Document Type | Management | Classification | Internal
Version | 1.0 | Release Date
Author | Name
Designation
Reviewer | Name
Designation
Approver | Name
Designation
Revision History
Version | Revision Description |  | Release Date
1.0 | Initial Release
Document Distribution
Name | Department | Designation | Company
Employee 1 | Information Technology | System Administrator | HackTech
Employee 2 | Delivery | VP | HackTech
Employee 3 | HR | Manager | HackTech
Employee 4 | Admin | Manager | HackTech

## New Controls
New Controls
Classification | ISO/IEC 27001:2022 Control Identifier | Control Name | Objective evidence: Policy / Procedure | Tools, other artefacts | Remark | Status
New | 5.23 | Information security for the use of cloud services | Cloud Security Procedure – HT-ISMS-SOP-32 | Tools- Sophos Firewall, ZAP (pentesting), Seqrite AV | HackTech Already has Cloud Security Policy & Procedure | Implemented
New | 5.3 | ICT readiness for business continuity | BCP_DR Procedure – HT-ISMS-SOP-21 | Test Plan & Result | HackTech Already has BCP-DR Policy & Procedure | Implemented
New | 5.7 | Threat intelligence | Threat Intelligence Policy & Threat Intelligence Procedure – NEW | Newsletter- Cert IN, SOC radar Tools- ManageEngine | New Policy & Procedure to make | Planned
New | 7.4 | Physical security monitoring | Physical and Environmental Security Policy – HT-ISMS-PL-09 | Physical Tool – CCTV, Biometric system Entry – Visitor register | HackTech already has Policy but updation required. Update the section “Physical security Monitoring” in the doc “Clusion Physical and Environment Security policy.docx” | In-Progess
New | 8.1 | Information deletion | Information Deletion Policy – NEW |  | New Policy & Procedure to make | Planned
New | 8.11 | Data masking | Data Masking Policy & Data Masking Procedure – NEW | Data masking API | New Policy & Procedure to make | Planned
New | 8.12 | Data leakage prevention | Data Leakage Prevention Policy & Data Leakage Prevention Procedure -NEW | Seqrite Web DLP | HackTech already has Data Leakage Prevention Policy New Procedure to make | Planned
New | 8.16 | Monitoring activities | Monitoring Policy – HT-ISMS-PL-20 | Logs from the following tools are been monitored by sys admin reviewed by director 1. Sophos firewall 2. Manage Engine 3. Sequrite | HackTech already has Monitoring Policy. | Implemented
New | 8.23 | Web filtering | Web Filter Policy & Procedure– NEW | 1. Policies configured in Firewall 2. Cloud- Native firewall | New Policy & Procedure to make | Planned
New | 8.28 | Secure coding | Access Control Procedure – HT-ISMS-SOP-02 | 1. Bitbucket 2.SAST & DAST Reports 3. Awarness Sessions | HackTech already has this topic covered in Access Control Procedure doc. | Implemented
New | 8.9 | Configuration management | Configuration Management Policy & Configuration Management Procedure – NEW | 1. Gross block 2. Manage Engine | New Policy & Procedure to make | Planned

## Merged Controls
Merged Controls
ISO/IEC 27001:2022 Control Identifier | ISO/IEC 27001:2013 Control Identifier | Control Name | Objective evidence: Policy / Procedure | Tools, other artefacts | Remark | Status
5.1 | 5.1.1,5.1.2 | Policies For Information Security | Information Security Policy – HT-ISMS-MN-02 | Internal Review of Documents Annualy |  | Implemented
5.1 | 8.1.3,8.2.3 | Acceptable use of information and other associated assets | Acceptable Use Policy – HT-ISMS-PL-02 | Internal Review of Documents Annualy |  | Implemented
5.14 | 13.2.1,13.2.2,13.2.3 | Information transfer | Communications Security Procedure – HT-ISMS-SOP-09 | Review of Documents Annualy |  | Implemented
5.15 | 9.1.1.,9.1.2 | Access control | Access Control Policy – HT-ISMS-PL-04 & Access Control Procedure – HT-ISMS-SOP-02 | Tools- Sophos, Seqrite, Manage Engine. Internal Review of Documents Annualy |  | Implemented
5.17 | 9.2.4,9.3.1,9.4.3 | Authentication information | Password Policy – HT-ISMS-PL-03 | Seqrite Internal Review of Documents Annualy |  | Implemented
5.18 | 9.2.2,9.2.5,9.2.6 | Access rights | Access Control Policy – HT-ISMS-PL-04 & Access Control Procedure – HT-ISMS-SOP-02 | Tools- Sophos, Seqrite, Manage Engine. Internal Review of Documents Annualy |  | Implemented
5.22 | 15.2.1,15.2.2 | Monitoring,review and change management of supplier services | Monitoring Policy – HT-ISMS-PL-20 & Logging & Monitoring Procedure – HT-ISMS-SOP-14 | Internal Review of Documents Annualy |  | Implemented
5.29 | 17.1.1,17.1.2,17.1.3 | Information security during disruption | BCP_DR Procedure – HT-ISMS-SOP-21 | Sophos, Router Internal Review of Documents Annualy |  | Implemented
5.31 | 18.1.1.,18.1.5 | Legal,statutory,regulatory and contractual requirements | Legal Regulatory Requirements and Compliance Procedure – HT-ISMS-SOP-26 | Internal Review of Documents Annualy |  | Implemented
5.36 | 18.2.2,18.2.3 | Compliance with policies,rules and standards for information security | Legal Regulatory Requirements and Compliance Procedure – HT-ISMS-SOP-26 | Internal Review of Documents Annualy |  | Implemented
5.8 | 6.1.15,14.1.1 | Information Security in project management | Vulnerability Management Procedure – HT-ISMS-SOP-20 | ZAP Internal Review of Documents Annualy |  | Implemented
5.9 | 8.1..1,8.1.2 | Inventory of information and other associated assets | Asset Management Policy – HT-ISMS-PL-05 | Internal Review of Documents Annualy |  | Implemented
6.8 | 16.1.2,16.1.3 | Information security event reporting | Security Incident Management Procedure – HT-ISMS-SOP-19 | Sophos, Seqrite Internal Review of Documents Annualy |  | Implemented
7.1 | 8.3.1,8.3.2,8.3.3, 11.2.5 | Storage media | Asset Management Policy – HT-ISMS-PL-05 | Internal Review of Documents Annualy |  | Implemented
7.2 | 11.1.2,11.1.6 | Physical entry | Physical and Environmental Security Policy – HT-ISMS-PL-09 | Physical Tool – Biometric system, CCTV Entry – Visitor register Internal Review of Documents Annualy |  | Implemented
8.1 | 6.2.1,11.2.8 | User endpoint devices | Organisation of Information Security – HT-ISMS-MN-04 Physical and Environmental Security Policy – HT-ISMS-PL-09 | Internal Review of Documents Annualy |  | Implemented
8.15 | 12.4.1,12.4.2,12.4.3 | Logging | Monitoring Policy – HT-ISMS-PL-20 Operations Security Procedure – HT-ISMS-SOP-16 Logging & Monitoring Procedure – HT-ISMS-SOP-14 | Sophos, Manage Engine Internal Review of Documents Annualy |  | Implemented
8.19 | 12.5.1,12.6.2 | Installation of software on operational systems | Operations Security Procedure – HT-ISMS-SOP-16 Configuration Management Policy Configuration Management Procedure – NEW | Sophos, Manage Engine Internal Review of Documents Annualy |  | Implemented
8.24 | 10.1.1,10.1.2 | Use of cryptography | Cryptography and Key Managment Policy – HT-ISMS-PL-07 | Internal Review of Documents Annualy |  | Implemented
8.26 | 14.1.2,14.1.3 | Application security requirements | System Acquisition Development and Maintenance Policy – HT-ISMS-PL-11 Vulnerability Management Procedure – HT-ISMS-SOP-20 | ZAP Internal Review of Documents Annualy |  | Implemented
8.29 | 14.2.8,14.2.9 | Security testing in development and acceptance | System Acquisition Development and Maintenance Policy – HT-ISMS-PL-11 Vulnerability Management Procedure – HT-ISMS-SOP-20 | ZAP Internal Review of Documents Annualy |  | Implemented
8.31 | 12.1.4,14.2.6 | Separation of development,test and production environments | Operations Security Procedure – HT-ISMS-SOP-16 System Acquisition Development and Maintenance Policy – HT-ISMS-PL-11 | Sophos, Manage Engine Internal Review of Documents Annualy |  | Implemented
8.32 | 12.1.2,14.2.2,14.2.3, 14.2.4 | Change management | Change Management Procedure – HT-ISMS-SOP-04 | Internal Review of Documents Annualy |  | Implemented
8.8 | 12.6.1,18.2.3 | Management of technical vulnerabilities | Operations Security Procedure – HT-ISMS-SOP-16 Legal Regulatory Requirements and Compliance Procedure – HT-ISMS-SOP-26 Vulnerability Management Procedure – HT-ISMS-SOP-20 | Sophos, Manage Engine Internal Review of Documents Annualy |  | Implemented